## Overview
Intelligent Disaster Response & Emergency Coordination Platform
Final-year B.Tech major project ¦ Implementation plan workbook ¦ Yellow cells are inputs you can edit
1. PROJECT INFORMATION
Project title | AI-Driven, Event-Driven Disaster Response & Emergency Coordination Platform
Core idea | Collects citizen/team reports, classifies and prioritizes them with NLP/ML, detects duplicates, geocodes locations, and recommends resource allocation on a live command-center dashboard.
Approach | MVP-first, phased delivery (Agile, 1-week iterations). Each phase ends in a demo so a working project always exists.
2. PLANNING INPUTS (edit the yellow cells)
Project start date | 2026-10-19 | Assumption: Monday 19-Oct-2026. Change to your real start; all dates update.
Team size (people) | 4 | Assumption: 4 members. Edit to match your team.
Hours per person per week | 15 | Assumption: 15 h/week alongside classes. Edit to match reality.
3. LIVE PROJECT DASHBOARD (all formulas)
Total tasks | 75 | Rows in Task Plan
Tasks completed | 0 | Status = Done
Tasks blocked | 0 | Needs attention
Overall progress (effort-weighted) | 0% | Hours x % done / total hours
Planned end date | 2027-02-08 | Latest task end date
Planned duration (weeks) | 16.1 | From start date to planned end
Days to planned end | 118 | Recalculates daily
Total estimated effort (hours) | 842 | Sum of task estimates
Team capacity (hours) | 966 | Team size x hours/week x weeks
Capacity utilization | 87.16% | Above 100% = over-committed
Must-have effort (hours) | 644 | Minimum viable scope
Must-have utilization | 66.67% | If total is over 100%, cut 'Could' then 'Should' tasks
Scope health | On track: full scope fits |  | Auto assessment
4. HOW TO USE THIS WORKBOOK
Roadmap | Seven phases with goals, deliverables, exit criteria; dates and progress roll up from Task Plan.
Task Plan | Master backlog with MoSCoW priority, effort, dependencies and an auto-drawn weekly Gantt. Update Status, % Done and Assignee.
Tech Stack | Free / open-source component choices with rationale and alternatives (INR 0 budget).
Architecture | Service responsibilities and key design decisions to defend in viva.
Database | Table and column design including PostGIS and pgvector columns, plus indexes.
API Design | REST/WebSocket endpoints with role access, per phase.
AI-ML Plan | Models, datasets, metrics and targets; also the LLM usage policy.
Priority Model | Editable weights and a live calculator for the incident priority score.
Testing | Test strategy with tools and pass criteria.
Risks | Risk register with scoring and mitigation.
Viva Prep | Likely examiner questions with answer outlines.
Colour legend | Blue text / yellow fill = editable input. Black = formula or fixed content. Estimates are planning assumptions for a small student team, not measured values.

## Roadmap
Roadmap & Phase Summary
Dates, hours and progress are formulas driven by the Task Plan sheet
Phase | Phase Name | Goal | Key Deliverables | Exit Criteria / Milestone | Start | End | Weeks | Tasks | Est. Hours | Progress | Status
P0 | Planning & Approval | Get topic approved, freeze scope, finish SRS + HLD, set up tooling and data plan. | Approved proposal, SRS, HLD diagrams, ADRs, repo + CI skeleton, dataset plan | Guide signs off scope; Docker skeleton boots; SRS v1 reviewed | 2026-10-19 | 2026-11-01 | 2 | 10 | 92 | 0% | Not Started
P1 | MVP Core Platform | Working end-to-end product without AI: auth, RBAC, reporting, resources, dashboard, map. | Auth + RBAC, Incident API, Citizen portal, Authority dashboard v1, Resource CRUD, CI tests | Citizen files report -> Authority sees it on map -> status updated (demo M1) | 2026-11-02 | 2026-11-23 | 3.1 | 14 | 154 | 0% | Not Started
P2 | AI Layer (NLP + LLM) | Classification, severity, entity extraction, queue-based AI worker, LLM summaries. | Labeled dataset, category + severity models, extractor, AI worker, model evaluation report | Reports auto-classified asynchronously with confidence; F1 report ready (demo M2) | 2026-11-23 | 2026-12-14 | 3.1 | 12 | 148 | 0% | Not Started
P3 | Intelligent Engine | Duplicate detection, geocoding, priority scoring, resource allocation, assignment workflow. | Embedding + dedup service, geocoder, priority engine, allocation optimizer, rescue-team view | Duplicates merged; ranked feed; allocation recommendations approved & executed (demo M3) | 2026-12-14 | 2027-01-07 | 3.6 | 12 | 142 | 0% | Not Started
P4 | Advanced Features | Real-time command center, image analysis, NL queries, situation summaries, analytics. | WebSocket updates, command center, CV model, NL query, analytics, broadcast alerts | Live dashboard updates; image signal fused into severity; feature freeze (M4) | 2027-01-04 | 2027-01-18 | 2.1 | 9 | 106 | 0% | Not Started
P5 | Production Hardening | Containerize, secure, monitor, load-test, tune and deploy. | Docker Compose stack, Nginx, Redis limits, Prometheus/Grafana, load + security test reports, CI/CD | Load-test report with RPS/P95; zero critical security findings; one-command deploy | 2027-01-18 | 2027-01-31 | 2 | 10 | 102 | 0% | Not Started
P6 | Documentation & Viva | Final report, ML report, slides, scripted demo, mock vivas, buffer. | Final report, ML report, PPT, demo script + backup video, Q&A sheet | Two mock vivas done; demo runs offline from seeded data | 2027-01-18 | 2027-02-08 | 3.1 | 8 | 98 | 0% | Not Started
| TOTAL |  |  |  | 2026-10-19 | 2027-02-08 | 16.1 | 75 | 842 | 0%
Phases overlap by design (e.g. documentation starts while hardening). Version-1 principle: if time runs out after Phase 3, you still have a complete, demonstrable intelligent system.
Formulas:
Start = MINIFS('Task Plan'!$L5:L200,'Task Plan'!$B5:B200,[Phase])
Start = MIN(F5:[Start, row above])
End = MAXIFS('Task Plan'!$M5:M200,'Task Plan'!$B5:B200,[Phase])
End = MAX(G5:[End, row above])

## Task Plan
Master Task Plan & Weekly Gantt
Edit Assignee, Priority, Hours, Start Week, Weeks, Status, % Done (blue). Dates and Gantt update automatically. Priority: Must / Should / Could (MoSCoW)
[7 empty] | Total hrs | 842 | [8 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
ID | Phase | Phase Name | Task | Description | Role | Assignee | Priority | Est. Hours | Start Week | Weeks | Start Date | End Date | Depends On | Status | % Done | Deliverable | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01
T-001 | P0 | Planning & Approval | Finalize problem statement & scope | Write 1-page problem statement, in-scope / out-of-scope list, success metrics. | Team |  | Must | 6 | 1 | 0.5 | 2026-10-19 | 2026-10-22 |  | Not Started | 0% | Scope document
T-002 | P0 | Planning & Approval | Prepare topic-approval proposal | Abstract, architecture one-pager, novelty points and phase plan for the guide. | Team |  | Must | 6 | 1 | 1 | 2026-10-19 | 2026-10-25 | T-001 | Not Started | 0% | Proposal PDF
T-003 | P0 | Planning & Approval | Literature & existing-system survey | Study crisis informatics papers and tools such as Ushahidi and Sahana Eden; list gaps. | Team |  | Should | 12 | 1 | 2 | 2026-10-19 | 2026-11-01 |  | Not Started | 0% | Survey notes
T-004 | P0 | Planning & Approval | Requirements & SRS | Functional + non-functional requirements, use cases, user stories with acceptance criteria. | Team |  | Must | 16 | 1 | 2 | 2026-10-19 | 2026-11-01 | T-001 | Not Started | 0% | SRS v1
T-005 | P0 | Planning & Approval | Roles, personas & RBAC matrix | Define Citizen, Authority, Rescue Team, Admin permissions per endpoint/screen. | Backend |  | Must | 6 | 2 | 0.5 | 2026-10-26 | 2026-10-29 | T-004 | Not Started | 0% | RBAC matrix
T-006 | P0 | Planning & Approval | High-Level Design (HLD) | Context diagram, component diagram, data-flow, deployment diagram, sequence diagrams. | Lead |  | Must | 16 | 2 | 1 | 2026-10-26 | 2026-11-01 | T-004 | Not Started | 0% | HLD document
T-007 | P0 | Planning & Approval | Tech-stack finalization & ADRs | Record each major choice (FastAPI, RabbitMQ, pgvector...) as an Architecture Decision Record. | Lead |  | Should | 6 | 2 | 1 | 2026-10-26 | 2026-11-01 | T-006 | Not Started | 0% | ADR log
T-008 | P0 | Planning & Approval | Repository & workflow setup | Monorepo layout, branching strategy, PR template, pre-commit, GitHub Projects board. | DevOps |  | Must | 6 | 1 | 1 | 2026-10-19 | 2026-10-25 |  | Not Started | 0% | Repo + board
T-009 | P0 | Planning & Approval | Docker Compose skeleton | Postgres+PostGIS+pgvector, Redis, RabbitMQ, MinIO containers with health checks. | DevOps |  | Must | 8 | 2 | 1 | 2026-10-26 | 2026-11-01 | T-008 | Not Started | 0% | docker-compose.yml
T-010 | P0 | Planning & Approval | Dataset survey & collection plan | Shortlist public crisis datasets (text + image); license check; synthetic-data plan. | AI/ML |  | Must | 10 | 1 | 2 | 2026-10-19 | 2026-11-01 |  | Not Started | 0% | Dataset plan
T-011 | P1 | MVP Core Platform | Low-Level Design | ERD, OpenAPI contracts, module boundaries, error-handling and logging conventions. | Backend |  | Must | 14 | 3 | 1 | 2026-11-02 | 2026-11-08 | T-006 | Not Started | 0% | LLD + OpenAPI draft
T-012 | P1 | MVP Core Platform | Database migrations (Alembic) | Core tables, PostGIS geometry columns, indexes, seed data scripts. | Backend |  | Must | 10 | 3 | 1 | 2026-11-02 | 2026-11-08 | T-011 | Not Started | 0% | Migration scripts
T-013 | P1 | MVP Core Platform | Authentication service | Register/login, password hashing (argon2/bcrypt), JWT access + refresh tokens, logout. | Backend |  | Must | 14 | 3 | 1.5 | 2026-11-02 | 2026-11-12 | T-012 | Not Started | 0% | Auth module
T-014 | P1 | MVP Core Platform | RBAC middleware | Role-based dependency guards for all routes; deny-by-default; tests per role. | Backend |  | Must | 8 | 4 | 1 | 2026-11-09 | 2026-11-15 | T-013 | Not Started | 0% | RBAC guards
T-015 | P1 | MVP Core Platform | Incident reporting API | Create / list / get / update-status endpoints; pagination, filtering, validation. | Backend |  | Must | 14 | 4 | 1.5 | 2026-11-09 | 2026-11-19 | T-012 | Not Started | 0% | Incident API
T-016 | P1 | MVP Core Platform | Secure media upload | MIME + size validation, random filenames, MinIO storage, signed URLs. | Backend |  | Should | 10 | 4 | 1 | 2026-11-09 | 2026-11-15 | T-009 | Not Started | 0% | Upload module
T-017 | P1 | MVP Core Platform | Frontend scaffold | React + Vite + TypeScript, routing, auth flow, layout, UI kit. | Frontend |  | Must | 12 | 3 | 1.5 | 2026-11-02 | 2026-11-12 | T-011 | Not Started | 0% | Frontend skeleton
T-018 | P1 | MVP Core Platform | Citizen portal | Report form with browser geolocation, image upload, report tracking page. | Frontend |  | Must | 16 | 4 | 2 | 2026-11-09 | 2026-11-22 | T-017 | Not Started | 0% | Citizen UI
T-019 | P1 | MVP Core Platform | Authority dashboard v1 | Incident table, filters, detail drawer, verify / status-change actions. | Frontend |  | Must | 14 | 4 | 2 | 2026-11-09 | 2026-11-22 | T-017 | Not Started | 0% | Authority UI v1
T-020 | P1 | MVP Core Platform | Map view v1 | Leaflet + OpenStreetMap markers coloured by severity; click-through to incident. | Frontend |  | Must | 10 | 5 | 1 | 2026-11-16 | 2026-11-22 | T-019 | Not Started | 0% | Map component
T-021 | P1 | MVP Core Platform | Resource & rescue-team management | CRUD for ambulances, boats, teams, kits; availability status; location. | Full-stack |  | Must | 12 | 5 | 1 | 2026-11-16 | 2026-11-22 | T-014 | Not Started | 0% | Resource module
T-022 | P1 | MVP Core Platform | Audit logging & input validation | Append-only audit log for sensitive actions; strict Pydantic schemas. | Backend |  | Should | 6 | 4 | 1 | 2026-11-09 | 2026-11-15 | T-015 | Not Started | 0% | Audit log
T-023 | P1 | MVP Core Platform | MVP tests + CI pipeline | pytest unit/API tests, lint, GitHub Actions on every PR. | DevOps |  | Must | 10 | 5 | 1 | 2026-11-16 | 2026-11-22 | T-015 | Not Started | 0% | CI green
T-024 | P1 | MVP Core Platform | Milestone M1: MVP demo | Demo to guide; collect feedback; update backlog. | Team |  | Must | 4 | 5.5 | 0.5 | 2026-11-20 | 2026-11-23 | T-023 | Not Started | 0% | Demo + feedback notes
T-025 | P2 | AI Layer (NLP + LLM) | Build labeled dataset | Map public crisis datasets to own taxonomy (medical, rescue, infrastructure, fire, flood, other) and severity. | AI/ML |  | Must | 16 | 6 | 1 | 2026-11-23 | 2026-11-29 | T-010 | Not Started | 0% | Labeled CSV + data card
T-026 | P2 | AI Layer (NLP + LLM) | Synthetic report generator | Templates + local LLM to create English/Hinglish reports with known labels for gaps. | AI/ML |  | Should | 12 | 6 | 1 | 2026-11-23 | 2026-11-29 | T-010 | Not Started | 0% | Generator script
T-027 | P2 | AI Layer (NLP + LLM) | Text preprocessing pipeline | Cleaning, emoji handling, Hinglish normalization, tokenization, train/val/test split. | AI/ML |  | Must | 8 | 6 | 1 | 2026-11-23 | 2026-11-29 | T-025 | Not Started | 0% | Preprocess module
T-028 | P2 | AI Layer (NLP + LLM) | Incident category classifier | TF-IDF + Logistic Regression baseline, then fine-tuned DistilBERT / MiniLM; compare. | AI/ML |  | Must | 20 | 7 | 1.5 | 2026-11-30 | 2026-12-10 | T-027 | Not Started | 0% | Category model v1
T-029 | P2 | AI Layer (NLP + LLM) | Severity classifier | Text + engineered features (people count, keywords, medical flag) -> LOW/MEDIUM/HIGH/CRITICAL. | AI/ML |  | Must | 16 | 7 | 1.5 | 2026-11-30 | 2026-12-10 | T-027 | Not Started | 0% | Severity model v1
T-030 | P2 | AI Layer (NLP + LLM) | Entity extraction | People count, location phrase, resource need via regex rules + NER fallback. | AI/ML |  | Must | 16 | 7 | 1.5 | 2026-11-30 | 2026-12-10 | T-027 | Not Started | 0% | Extractor module
T-031 | P2 | AI Layer (NLP + LLM) | Model evaluation | Precision/recall/F1, confusion matrix, per-class error analysis, calibration check. | AI/ML |  | Must | 8 | 8 | 1 | 2026-12-07 | 2026-12-13 | T-028, T-029 | Not Started | 0% | Evaluation report
T-032 | P2 | AI Layer (NLP + LLM) | Model serving & versioning | Model loader with versioned artifacts and MLflow (or file-based) registry. | AI/ML |  | Should | 12 | 8 | 1 | 2026-12-07 | 2026-12-13 | T-028 | Not Started | 0% | Model registry
T-033 | P2 | AI Layer (NLP + LLM) | Queue integration | API -> RabbitMQ -> AI worker -> DB; idempotent consumers, retries, dead-letter queue. | Backend |  | Must | 16 | 7 | 2 | 2026-11-30 | 2026-12-13 | T-015, T-030 | Not Started | 0% | Async pipeline
T-034 | P2 | AI Layer (NLP + LLM) | LLM summarization (Ollama) | Summarize clusters of reports with prompt guardrails and length limits; runs locally. | AI/ML |  | Should | 12 | 8 | 1 | 2026-12-07 | 2026-12-13 | T-033 | Not Started | 0% | Summary service
T-035 | P2 | AI Layer (NLP + LLM) | Store predictions + human override | Save model, label, confidence in ai_predictions; authority can correct and log override. | Full-stack |  | Must | 8 | 8 | 1 | 2026-12-07 | 2026-12-13 | T-033 | Not Started | 0% | Override flow
T-036 | P2 | AI Layer (NLP + LLM) | Milestone M2: AI demo | Show async classification with confidence on live submissions. | Team |  | Must | 4 | 8.5 | 0.5 | 2026-12-11 | 2026-12-14 | T-031, T-035 | Not Started | 0% | Demo + metrics
T-037 | P3 | Intelligent Engine | Embedding service + pgvector | Multilingual MiniLM embeddings stored in pgvector; ANN index (HNSW/IVFFlat). | AI/ML |  | Must | 12 | 9 | 1 | 2026-12-14 | 2026-12-20 | T-033 | Not Started | 0% | Embedding service
T-038 | P3 | Intelligent Engine | Duplicate detection & clustering | Cosine similarity + geo-radius + time-window rules; merge into canonical incident. | AI/ML |  | Must | 16 | 9.5 | 1.5 | 2026-12-18 | 2026-12-28 | T-037 | Not Started | 0% | Dedup engine
T-039 | P3 | Intelligent Engine | Threshold tuning | Tune similarity threshold on labeled duplicate pairs; report precision/recall trade-off. | AI/ML |  | Should | 8 | 11 | 0.5 | 2026-12-28 | 2026-12-31 | T-038 | Not Started | 0% | Tuning report
T-040 | P3 | Intelligent Engine | Geocoding pipeline | Nominatim lookup with Redis cache, rate-limit compliance, local gazetteer fallback. | Backend |  | Must | 12 | 9 | 1 | 2026-12-14 | 2026-12-20 | T-030 | Not Started | 0% | Geocoder
T-041 | P3 | Intelligent Engine | Priority scoring engine | Configurable weighted score (see Priority Model sheet); explainable breakdown per incident. | Backend |  | Must | 14 | 10 | 1 | 2026-12-21 | 2026-12-27 | T-029, T-038 | Not Started | 0% | Priority engine
T-042 | P3 | Intelligent Engine | Ranked incident feed | Redis sorted set for live priority queue; re-score on new reports and waiting time. | Backend |  | Must | 8 | 10.5 | 0.5 | 2026-12-25 | 2026-12-28 | T-041 | Not Started | 0% | Ranked feed
T-043 | P3 | Intelligent Engine | Resource allocation optimizer | Min-cost assignment (Hungarian) using travel distance; capacity and type constraints. | AI/ML |  | Must | 20 | 10 | 1.5 | 2026-12-21 | 2026-12-31 | T-021, T-041 | Not Started | 0% | Allocator
T-044 | P3 | Intelligent Engine | Assignment workflow | Recommend -> authority approves -> team accepts -> in-progress -> completed. | Full-stack |  | Must | 14 | 11 | 1 | 2026-12-28 | 2027-01-03 | T-043 | Not Started | 0% | Workflow
T-045 | P3 | Intelligent Engine | Rescue-team mobile view (PWA) | Mobile-friendly screens: assignments, navigation link, status updates, field notes. | Frontend |  | Should | 14 | 11 | 1.5 | 2026-12-28 | 2027-01-07 | T-044 | Not Started | 0% | PWA
T-046 | P3 | Intelligent Engine | Scenario simulation harness | Generate flood-event traffic with ground truth to test the whole pipeline. | AI/ML |  | Should | 10 | 9 | 1 | 2026-12-14 | 2026-12-20 | T-026 | Not Started | 0% | Simulator
T-047 | P3 | Intelligent Engine | Engine tests | Unit + property-based tests for priority and allocation; regression on simulated scenarios. | Backend |  | Must | 10 | 11 | 1 | 2026-12-28 | 2027-01-03 | T-041, T-043 | Not Started | 0% | Test suite
T-048 | P3 | Intelligent Engine | Milestone M3: Intelligence demo | End-to-end: reports -> dedup -> priority -> allocation. | Team |  | Must | 4 | 11.5 | 0.5 | 2027-01-01 | 2027-01-04 | T-044, T-047 | Not Started | 0% | Demo
T-049 | P4 | Advanced Features | Real-time updates | WebSocket/SSE channel pushing new incidents, status and resource changes. | Backend |  | Must | 12 | 12 | 1 | 2027-01-04 | 2027-01-10 | T-044 | Not Started | 0% | Realtime gateway
T-050 | P4 | Advanced Features | Command-center dashboard | KPIs, heatmap, clusters, resource panel, live feed, filters by zone. | Frontend |  | Must | 20 | 12 | 2 | 2027-01-04 | 2027-01-17 | T-049 | Not Started | 0% | Command center
T-051 | P4 | Advanced Features | Image classification model | Fine-tune MobileNetV3/EfficientNet-B0 on public flood/damage images. | AI/ML |  | Should | 20 | 12 | 2 | 2027-01-04 | 2027-01-17 | T-010 | Not Started | 0% | CV model
T-052 | P4 | Advanced Features | CV worker + signal fusion | Run CV in worker; fuse flood/damage score into severity and priority. | AI/ML |  | Should | 10 | 13 | 1 | 2027-01-11 | 2027-01-17 | T-051 | Not Started | 0% | CV integration
T-053 | P4 | Advanced Features | Natural-language query | Authority types a query; LLM outputs a validated JSON filter; no raw SQL generated. | AI/ML |  | Could | 14 | 12.5 | 1 | 2027-01-08 | 2027-01-14 | T-034 | Not Started | 0% | NL query
T-054 | P4 | Advanced Features | Situation summary | On-demand 'what is happening now' summary grounded in current DB stats. | AI/ML |  | Could | 8 | 13 | 0.5 | 2027-01-11 | 2027-01-14 | T-034 | Not Started | 0% | Summary endpoint
T-055 | P4 | Advanced Features | Analytics module | Response time, resolution time, hotspots, resource utilization reports. | Full-stack |  | Should | 10 | 13 | 1 | 2027-01-11 | 2027-01-17 | T-044 | Not Started | 0% | Analytics page
T-056 | P4 | Advanced Features | Broadcast alerts | Authority announcements visible to citizens by zone. | Full-stack |  | Could | 8 | 13 | 0.5 | 2027-01-11 | 2027-01-14 | T-049 | Not Started | 0% | Announcements
T-057 | P4 | Advanced Features | Milestone M4: Feature freeze | Freeze scope; only bug-fixes after this point. | Team |  | Must | 4 | 13.5 | 0.5 | 2027-01-15 | 2027-01-18 | T-050 | Not Started | 0% | Freeze tag
T-058 | P5 | Production Hardening | Dockerize all services | Multi-stage images, non-root users, compose profiles for dev/prod. | DevOps |  | Must | 12 | 14 | 1 | 2027-01-18 | 2027-01-24 | T-057 | Not Started | 0% | Compose stack
T-059 | P5 | Production Hardening | Nginx reverse proxy + TLS | Routing, gzip, security headers, CORS policy, TLS (self-signed or Let's Encrypt). | DevOps |  | Must | 8 | 14 | 0.5 | 2027-01-18 | 2027-01-21 | T-058 | Not Started | 0% | Nginx config
T-060 | P5 | Production Hardening | Redis caching & rate limiting | Cache hot reads; token-bucket rate limits per role (e.g. citizen reports/min). | Backend |  | Must | 10 | 14 | 1 | 2027-01-18 | 2027-01-24 | T-057 | Not Started | 0% | Cache + limits
T-061 | P5 | Production Hardening | Observability | Prometheus metrics, Grafana dashboards, structured JSON logs, queue-depth alerts. | DevOps |  | Must | 12 | 14 | 1 | 2027-01-18 | 2027-01-24 | T-058 | Not Started | 0% | Grafana dashboards
T-062 | P5 | Production Hardening | Load testing | Locust/k6: ~1000 virtual users, ~10k reports; record RPS, P95, queue lag, inference time. | DevOps |  | Must | 14 | 15 | 1 | 2027-01-25 | 2027-01-31 | T-060, T-061 | Not Started | 0% | Load-test report
T-063 | P5 | Production Hardening | Performance tuning | EXPLAIN-driven indexes, worker concurrency, batch inference, connection pools. | Backend |  | Should | 10 | 15 | 1 | 2027-01-25 | 2027-01-31 | T-062 | Not Started | 0% | Tuning notes
T-064 | P5 | Production Hardening | Security testing | OWASP Top-10 checklist, ZAP baseline scan, dependency audit, secrets scan. | Backend |  | Must | 10 | 14.5 | 1 | 2027-01-22 | 2027-01-28 | T-058 | Not Started | 0% | Security report
T-065 | P5 | Production Hardening | Resilience testing | Kill worker/DB/broker mid-load; verify retries, DLQ and recovery. | DevOps |  | Should | 8 | 15 | 0.5 | 2027-01-25 | 2027-01-28 | T-062 | Not Started | 0% | Resilience report
T-066 | P5 | Production Hardening | CI/CD pipeline | Build, test, lint, scan, push images to GHCR; tagged releases. | DevOps |  | Should | 8 | 14 | 1 | 2027-01-18 | 2027-01-24 | T-023 | Not Started | 0% | Pipeline
T-067 | P5 | Production Hardening | Deployment | Deploy on local/college server or a free-tier VM if available; runbook + backup script. | DevOps |  | Must | 10 | 15 | 1 | 2027-01-25 | 2027-01-31 | T-057, T-065 | Not Started | 0% | Live deployment
T-068 | P6 | Documentation & Viva | Final SRS / HLD / LLD | Update design docs to match what was actually built. | Team |  | Must | 16 | 14 | 2 | 2027-01-18 | 2027-01-31 | T-044 | Not Started | 0% | Design docs
T-069 | P6 | Documentation & Viva | ML report | Datasets, models, metrics, limitations, bias and ethics, failure cases. | AI/ML |  | Must | 10 | 15 | 1 | 2027-01-25 | 2027-01-31 | T-031 | Not Started | 0% | ML report
T-070 | P6 | Documentation & Viva | Final project report | Thesis-format report with results, screenshots, test evidence, future work. | Team |  | Must | 24 | 15 | 2 | 2027-01-25 | 2027-02-07 | T-062, T-063 | Not Started | 0% | Report PDF
T-071 | P6 | Documentation & Viva | Presentation & poster | Slide deck and one-page architecture poster. | Team |  | Must | 10 | 16 | 1 | 2027-02-01 | 2027-02-07 | T-070 | Not Started | 0% | PPT + poster
T-072 | P6 | Documentation & Viva | Demo script & backup video | Scripted disaster scenario on seeded data; offline fallback and screen recording. | Team |  | Must | 10 | 16 | 1 | 2027-02-01 | 2027-02-07 | T-067 | Not Started | 0% | Demo script + video
T-073 | P6 | Documentation & Viva | Mock vivas | Two mock vivas using the Viva Prep sheet; fix weak answers. | Team |  | Must | 8 | 16 | 0.5 | 2027-02-01 | 2027-02-04 | T-072 | Not Started | 0% | Q&A notes
T-074 | P6 | Documentation & Viva | Buffer: bug-fixing & polish | Reserved slack for overruns, UI polish, last-minute fixes. | Team |  | Must | 16 | 15.5 | 1.5 | 2027-01-29 | 2027-02-08 |  | Not Started | 0% | Stable release
T-075 | P6 | Documentation & Viva | Final submission & evaluation | Submit report/code; present to evaluation committee. | Team |  | Must | 4 | 16.5 | 0.5 | 2027-02-05 | 2027-02-08 | T-074 | Not Started | 0% | Submitted
Add new tasks in the next empty row below the last task; formulas on Overview/Roadmap read rows 5-200. Copy the formulas in Phase Name, Start Date and End Date from the row above.

## Tech Stack
Technology Stack (INR 0 budget)
All components are free/open-source. Versions are suggestions; confirm licences and free-tier limits before relying on them.
Layer | Component | Choice | Why this choice | Cost | Alternative
Backend API | Web framework | FastAPI (Python 3.11) | Async, auto OpenAPI docs, same language as the ML code so models load in-process or in workers. | Free | NestJS (Node) + separate Python ML service
Backend | Background jobs | Celery workers on RabbitMQ | Mature task queue with retries, ack/nack, routing and dead-letter support. | Free | Dramatiq, RQ, plain pika consumers
Backend | ORM & migrations | SQLAlchemy 2 + Alembic | Typed models, versioned schema migrations. | Free | Prisma (Node), Django ORM
Data | Primary database | PostgreSQL 16 + PostGIS + pgvector | One database for relational, geospatial and vector data; fewer moving parts to run and explain. | Free | Qdrant for vectors, MongoDB for raw reports
Data | Cache / rate limit / live ranking | Redis 7 | Hot-read cache, token-bucket rate limits, sorted-set priority feed, pub/sub for realtime fan-out. | Free | Memcached (no sorted sets)
Data | Message broker | RabbitMQ 3 | Durable queues, acknowledgements, DLQ; easy to demo in management UI. | Free | Kafka (heavier; justify only if streaming scale is a goal)
Data | Object storage | MinIO (S3-compatible) | Stores incident images and documents; signed URLs. | Free | Local volume for dev
Frontend | Web app | React + Vite + TypeScript | Fast dev loop, strong typing, large ecosystem. | Free | Next.js
Frontend | Maps | Leaflet + OpenStreetMap | No paid map API. Respect OSM tile usage policy or use a self-hosted/permitted tile source for heavier use. | Free | MapLibre GL
Frontend | UI & charts | Tailwind CSS + Recharts | Rapid professional UI and dashboard charts. | Free | MUI, Chart.js
Realtime | Live updates | WebSocket (FastAPI) / SSE with Redis pub/sub | Push new incidents and status changes to the command center. | Free | Socket.IO
AI / ML | Classical ML & NLP | scikit-learn, Hugging Face Transformers | Baselines (TF-IDF + LR) and fine-tuned small transformers. | Free | spaCy pipelines
AI / ML | Embeddings | sentence-transformers (multilingual MiniLM) | Handles English/Hinglish similarity for duplicate detection; runs on CPU. | Free | BGE-small, E5-small
AI / ML | LLM (local) | Ollama + small open model (e.g. Llama 3.2 3B / Qwen2.5 3B-7B) | Local inference, no API bill; size chosen to fit your laptop RAM. | Free | llama.cpp directly
AI / ML | Computer vision | PyTorch + torchvision (MobileNetV3 / EfficientNet-B0) | Lightweight fine-tuning for flood/damage image classes on CPU or free Colab GPU. | Free (Colab free tier) | YOLO family (check licence)
AI / ML | Experiment tracking | MLflow | Track runs, metrics, artifacts; supports model versioning story. | Free | Weights & Biases free tier
Geo | Geocoding | Nominatim (OpenStreetMap) + Redis cache | Free geocoding; public instance has strict usage limits so cache aggressively or self-host a regional extract. | Free | Local gazetteer of city localities
Geo | Distance / routing | Haversine baseline; OSRM optional | Straight-line distance first; road routing as stretch goal. | Free | OpenRouteService free tier
Optimization | Resource allocation | SciPy linear_sum_assignment (Hungarian) | Optimal assignment under cost matrix; easy to explain and test. | Free | OR-Tools min-cost flow
DevOps | Containers & proxy | Docker + Docker Compose + Nginx | Reproducible one-command stack; TLS and routing at the edge. | Free | Podman, Caddy
DevOps | CI/CD | GitHub Actions + GHCR | Free CI minutes for student repos; image registry. | Free (usage limits apply) | GitLab CI
DevOps | Monitoring | Prometheus + Grafana | Metrics for RPS, latency, queue depth, inference time. | Free | Netdata, Loki for logs
Quality | Testing | pytest, Playwright, Locust (or k6), OWASP ZAP | Unit, API, E2E, load and security scanning. | Free | Postman/Newman, JMeter
Security | Auth & hardening | JWT (PyJWT) + argon2/bcrypt, token-bucket limits, security headers | Stateless auth with refresh tokens; deny-by-default RBAC. | Free | Keycloak (heavier IdP)
Docs | Diagrams & API docs | draw.io / Mermaid, Swagger UI | Architecture diagrams and live API documentation. | Free | PlantUML
Hosting | Where it runs | Local machine / college server; free-tier VM if available | Zero-budget deployment; keep a recorded demo as fallback because free tiers can change. | Free | Render/Railway free tiers (limits apply)

## Architecture
Architecture: Services & Design Decisions
Section A: services. Section B (below): decisions to defend in viva.
Service / Module | Responsibility | Technology | Talks To | Data Store | Scales By | Phase
API Gateway / Nginx | TLS termination, routing, rate limiting at edge, static frontend. | Nginx | API service, Frontend | - | Replicas behind load balancer | P5
API Service (modular monolith) | Auth, RBAC, incidents, resources, assignments, analytics as separate internal modules with clean boundaries. | FastAPI | Postgres, Redis, RabbitMQ, MinIO | PostgreSQL | Stateless replicas | P1
Auth module | Registration, login, JWT access/refresh, role checks, audit entries. | FastAPI module | Postgres, Redis | PostgreSQL | Stateless | P1
Incident module | Accept reports, return immediately (HTTP 202), publish event to queue. | FastAPI module | RabbitMQ, Postgres | PostgreSQL | Stateless; queue absorbs bursts | P1
NLP AI Worker | Classify category, severity, extract entities; write predictions with confidence. | Celery + scikit-learn/Transformers | RabbitMQ, Postgres | PostgreSQL | More worker processes | P2
Embedding & Dedup Worker | Create embeddings, search pgvector, merge duplicates by similarity + geo + time. | Celery + sentence-transformers | Postgres(pgvector), Redis | PostgreSQL | Worker replicas | P3
Geo Worker | Geocode location phrases, cache results, compute zones/clusters. | Celery + Nominatim client | Redis, Postgres(PostGIS) | PostgreSQL + Redis | Worker replicas (respect rate limit) | P3
Priority & Allocation Engine | Compute priority score, maintain ranked feed, recommend resource assignments. | Python + SciPy | Redis, Postgres | Redis + PostgreSQL | Stateless compute | P3
CV Worker | Flood/damage image classification; returns signals for fusion. | Celery + PyTorch | MinIO, RabbitMQ, Postgres | MinIO + PostgreSQL | GPU/CPU workers | P4
LLM Service | Summaries and NL-to-filter conversion using local model; output validated against schema. | Ollama | API service | - | Dedicated host/queue | P2
Realtime Gateway | Push live events to dashboards. | FastAPI WebSocket + Redis pub/sub | Redis, Frontend | Redis | Sticky sessions or pub/sub fan-out | P4
Observability stack | Collect metrics, dashboards, alerts. | Prometheus + Grafana | All services | Prometheus TSDB | - | P5
B. KEY DESIGN DECISIONS
Decision | Choice | Rationale | Trade-off / what to say if challenged
Architecture style | Modular monolith API + independent workers | Microservice-ready boundaries without the operational burden of 10+ deployables for a student team. | Less independent deploy per module; mitigated by queue-based workers and clean module interfaces.
Synchronous vs async ingest | Accept -> enqueue -> respond 202; process in workers | Disaster traffic is bursty; the queue absorbs spikes and decouples slow AI work from user latency. | Eventual consistency: classification appears seconds later; UI shows 'processing' state.
Delivery guarantees | At-least-once + idempotent consumers + DLQ | Prevents lost reports; duplicates handled by idempotency keys. | Requires idempotency design; exactly-once is not claimed.
Single DB for relational + vector + geo | PostgreSQL with PostGIS and pgvector | Fewer systems to operate; transactions across entities and embeddings. | Dedicated vector DB scales better at very large volume; not needed at project scale.
Where to use LLM | Only summaries and NL-to-filter; never as sole decision-maker | Classification/priority use cheaper, testable models; LLM output is validated and advisory. | LLM can hallucinate; guardrails, schema validation and human approval reduce risk.
Human in the loop | Authority approves allocations; can override AI labels | Safety-critical domain; builds trust and creates feedback data. | Slower than full automation; acceptable for emergency decisions.
Priority scoring | Transparent weighted formula (configurable) | Explainable to examiners and authorities; weights can be tuned. | Weights are judgment-based; show sensitivity analysis.
Resource allocation | Hungarian assignment on distance cost matrix | Optimal under cost model; deterministic and testable. | Ignores traffic and road closures unless routing added.
Security | JWT + deny-by-default RBAC + rate limits + audit log | Protects role boundaries and prevents report flooding. | Public reporting endpoint needs abuse controls (CAPTCHA/phone verify) as future work.
Caching | Redis for hot reads and ranked feed with explicit TTL/invalidation | Reduces DB load on dashboards. | Stale data risk; keep short TTLs and event-based invalidation.

## Database
Database Design (PostgreSQL + PostGIS + pgvector)
Logical design for implementation; refine in LLD. Add indexes on foreign keys and common filters.
Table | Column | Type | Constraints / Index | Notes
users | id | UUID | PK | Unique user id
users | name | VARCHAR(120) | NOT NULL | Full name
users | email | VARCHAR(255) | UNIQUE, NOT NULL | Login id
users | phone | VARCHAR(20) | NULL | For verification/alerts
users | password_hash | VARCHAR(255) | NOT NULL | argon2/bcrypt hash only
users | role | ENUM | NOT NULL | citizen ¦ authority ¦ rescue ¦ admin
users | is_active | BOOLEAN | DEFAULT true | Soft disable
users | created_at | TIMESTAMPTZ | DEFAULT now() | Audit
incidents | id | UUID | PK | Canonical incident
incidents | title | VARCHAR(200) | NOT NULL | Short title
incidents | description | TEXT | NOT NULL | Merged/primary description
incidents | category | ENUM | NULL | medical¦rescue¦infrastructure¦fire¦flood¦other
incidents | severity | ENUM | NULL | LOW¦MEDIUM¦HIGH¦CRITICAL
incidents | people_affected | INT | DEFAULT 0 | Extracted or reported
incidents | priority_score | NUMERIC(5,2) | INDEX | 0-100 from priority engine
incidents | location | GEOGRAPHY(Point,4326) | GiST INDEX | PostGIS point
incidents | location_text | VARCHAR(255) | NULL | Original text phrase
incidents | status | ENUM | NOT NULL | new¦verified¦assigned¦in_progress¦resolved¦rejected
incidents | report_count | INT | DEFAULT 1 | Number of merged duplicate reports
incidents | zone_id | UUID | FK -> disaster_zones | Affected zone
incidents | created_at / updated_at | TIMESTAMPTZ | INDEX | Waiting time derives from created_at
incident_reports | id | UUID | PK | Raw citizen/team report
incident_reports | incident_id | UUID | FK -> incidents | Set after dedup
incident_reports | user_id | UUID | FK -> users | Reporter
incident_reports | raw_text | TEXT | NOT NULL | Original text, never altered
incident_reports | idempotency_key | VARCHAR(64) | UNIQUE | Prevents double processing
incident_reports | processing_state | ENUM | NOT NULL | queued¦processing¦done¦failed
incident_reports | created_at | TIMESTAMPTZ | INDEX | Receive time
report_embeddings | report_id | UUID | PK, FK | One embedding per report
report_embeddings | embedding | VECTOR(384) | HNSW/IVFFlat INDEX | Dimension depends on model
report_embeddings | model_version | VARCHAR(50) | NOT NULL | Reproducibility
media | id | UUID | PK | Image/document
media | report_id | UUID | FK | Parent report
media | object_key | VARCHAR(255) | NOT NULL | MinIO key
media | mime_type | VARCHAR(50) | CHECK allowed | Validated type
media | cv_label / cv_score | VARCHAR / REAL | NULL | CV worker output
ai_predictions | id | UUID | PK | Prediction record
ai_predictions | incident_id / report_id | UUID | FK | Target
ai_predictions | model_name / model_version | VARCHAR | NOT NULL | Traceability
ai_predictions | label | VARCHAR(50) | NOT NULL | Predicted class
ai_predictions | confidence | REAL | CHECK 0-1 | Probability
ai_predictions | overridden_by | UUID | FK -> users NULL | Human correction
resources | id | UUID | PK | Ambulance, boat, team, kit
resources | type | ENUM | NOT NULL | ambulance¦rescue_team¦boat¦medical_kit¦food_kit¦other
resources | name | VARCHAR(100) | NOT NULL | Display name/code
resources | status | ENUM | NOT NULL | available¦assigned¦offline
resources | location | GEOGRAPHY(Point,4326) | GiST INDEX | Last known position
resources | capacity | INT | DEFAULT 1 | People/units
assignments | id | UUID | PK | Allocation record
assignments | incident_id | UUID | FK | Target incident
assignments | resource_id | UUID | FK | Assigned resource
assignments | status | ENUM | NOT NULL | recommended¦approved¦accepted¦in_progress¦completed¦cancelled
assignments | recommended_cost | NUMERIC | NULL | Optimizer cost (e.g. km)
assignments | assigned_at / completed_at | TIMESTAMPTZ | NULL | Lifecycle times
disaster_zones | id / name / boundary | UUID / TEXT / GEOGRAPHY(Polygon) | PK, GiST | Zone polygons for filtering and analytics
announcements | id / zone_id / message / created_by | UUID / UUID / TEXT / UUID | FK | Broadcast alerts
audit_logs | id | BIGSERIAL | PK | Append-only
audit_logs | actor_id / action / entity / entity_id | UUID / TEXT | INDEX | Who did what
audit_logs | payload / created_at | JSONB / TIMESTAMPTZ | NOT NULL | Change details
Index plan: GiST on geography columns; HNSW/IVFFlat on embeddings; B-tree on (status, priority_score DESC), created_at, foreign keys; partial index on active incidents.

## API Design
API Design (REST + WebSocket)
All routes versioned under /api/v1 in implementation. Deny-by-default RBAC; every list endpoint paginated.
Method | Endpoint | Access (role) | Purpose | Phase
POST | /auth/register | Public | Create citizen account | P1
POST | /auth/login | Public | Return access + refresh token | P1
POST | /auth/refresh | Authenticated | Rotate access token | P1
POST | /auth/logout | Authenticated | Revoke refresh token | P1
GET | /users/me | Authenticated | Current profile | P1
GET/PATCH | /admin/users | Admin | List/modify users and roles | P1
POST | /incidents/reports | Citizen+ | Submit report (returns 202 + tracking id) | P1
GET | /incidents/reports/{id} | Owner, Authority | Track processing state | P1
POST | /media/upload-url | Citizen+ | Get signed upload URL; validate type/size | P1
GET | /incidents | Authority, Rescue | Paginated list with filters (status, severity, zone, bbox) | P1
GET | /incidents/{id} | Authority, Rescue | Detail with predictions, merged reports, score breakdown | P1
PATCH | /incidents/{id}/status | Authority | Verify / reject / resolve | P1
PATCH | /incidents/{id}/labels | Authority | Override AI category/severity (audited) | P2
GET/POST/PATCH | /resources | Authority, Admin | Manage resources and availability | P1
GET | /incidents/ranked | Authority | Priority-ranked feed (Redis) | P3
POST | /allocations/recommend | Authority | Run optimizer and return recommendations | P3
POST | /allocations/{id}/approve | Authority | Approve a recommendation | P3
GET | /assignments/mine | Rescue | Assigned incidents | P3
PATCH | /assignments/{id}/status | Rescue | Accept / start / complete | P3
GET | /zones | Authority, Admin | Zones as GeoJSON | P3
POST | /llm/summary | Authority | Summarize selected incidents / current situation | P2
POST | /llm/query | Authority | NL query -> validated structured filter | P4
WS | /ws/live | Authority, Rescue | Realtime incident/resource events | P4
GET | /analytics/overview | Authority, Admin | KPIs, response times, hotspots | P4
POST/GET | /announcements | Authority (POST), All (GET) | Broadcast alerts | P4
GET | /health, /metrics | Internal | Liveness/readiness and Prometheus metrics | P5

## AI-ML Plan
AI / ML Plan
Targets are planning goals to be validated experimentally; report actual numbers honestly in the ML report. Verify each dataset's licence and terms before use.
ID | Model | Input | Output | Approach | Dataset (free / public) | Metrics | Target | Phase
M1 | Incident category classifier | Report text | medical / rescue / infrastructure / fire / flood / other | TF-IDF+LogReg baseline; fine-tuned DistilBERT or MiniLM head | HumAID, CrisisNLP (Twitter crisis data) + own synthetic data | Macro-F1, per-class recall | Macro-F1 >= 0.75 (planning target) | P2
M2 | Severity classifier | Text + engineered features (people count, medical flag, trapped flag) | LOW / MEDIUM / HIGH / CRITICAL with probabilities | Gradient boosting or LogReg on text+features; compare with transformer | Labeled subset + synthetic; relabel with clear rubric | Recall on CRITICAL (prioritize), weighted-F1 | CRITICAL recall >= 0.85 (planning target) | P2
M3 | Entity extractor | Report text | people_count, location phrase, resource needed | Regex/rules + NER fallback; Hinglish number words | Hand-annotated sample (200-300 reports) | Exact-match / token F1 | F1 >= 0.80 on annotated set | P2
M4 | Duplicate detector | Report embedding + coordinates + time | same-incident decision | Cosine similarity on multilingual MiniLM + geo-radius + time window | Constructed duplicate pairs from clusters | Precision / recall at chosen threshold | Precision >= 0.90 at recall >= 0.70 | P3
M5 | Image classifier | Uploaded image | flood / damage / normal + score | Fine-tuned MobileNetV3 / EfficientNet-B0 | FloodNet (post-flood imagery), CrisisMMD, other public flood sets | Accuracy, F1, confusion matrix | F1 >= 0.80 on held-out set | P4
M6 | LLM summarizer & NL-to-filter | Cluster of reports / authority query | Short summary / JSON filter | Local open LLM via Ollama with schema-constrained prompts | n/a (zero-shot, prompt-engineered) | Human rubric on 30 samples; schema-valid rate | Schema-valid >= 95%; no unsupported facts in rubric review | P2/P4
LLM policy: LLM output is advisory, schema-validated, and never auto-triggers dispatch. Classification and priority use testable models. Always show confidence and allow human override.

## Priority Model
Incident Priority Score: Editable Model & Live Calculator
Score (0-100) = sum of weight x normalized factor. Change blue weights; examples recalculate.
A. WEIGHTS (must total 100) |  |  | B. NORMALIZATION RULES
Factor | Weight |  | Severity level | Value |  | People cap (n) | 10
Severity | 35 |  | LOW | 0.25 |  | Waiting cap (min) | 60
People affected | 20 |  | MEDIUM | 0.5 |  | People factor = MIN(people / cap, 1); Waiting factor = MIN(minutes / cap, 1); Life threat and Location risk are 0-1 inputs. Caps and weights are judgment-based assumptions: run a sensitivity check in the report.
Life threat | 20 |  | HIGH | 0.75
Resource need | 10 |  | CRITICAL | 1
Location risk | 5
Waiting time | 10
Total (check = 100) | 100 | OK
C. LIVE EXAMPLES (replace with your own scenarios)
Incident | Severity | People | Life threat (0-1) | Resource need (0-1) | Location risk (0-1) | Waiting (min) | Severity factor | People factor | Waiting factor | Priority score | Rank
Road blocked by fallen trees | MEDIUM | 0 | 0 | 0.3 | 0.4 | 25 | 0.5 | 0 | 0.41667 | 26.6667 | 4
Family trapped in flooded house | CRITICAL | 6 | 1 | 0.9 | 0.8 | 15 | 1 | 0.6 | 0.25 | 82.5 | 2
Hospital needs oxygen | CRITICAL | 20 | 1 | 1 | 0.6 | 10 | 1 | 1 | 0.16667 | 89.6667 | 1
Minor road damage | LOW | 0 | 0 | 0.1 | 0.2 | 40 | 0.25 | 0 | 0.66667 | 17.4167 | 5
Bridge collapse near market | HIGH | 3 | 0.5 | 0.7 | 0.9 | 30 | 0.75 | 0.3 | 0.5 | 58.75 | 3
Explainability: store the six weighted contributions per incident so the dashboard can show why an incident ranks where it does.

## Testing
Test Strategy & Acceptance Criteria
Numeric thresholds are planning targets; record measured results in the final report.
ID | Type | What is tested | Tool | Pass criteria | Phase
TS-01 | Unit | Auth, RBAC guards, validators, priority formula, allocator | pytest + coverage | Coverage >= 80% on core modules; all role-denial cases pass | P1-P3
TS-02 | API / integration | Incident lifecycle with real Postgres/Redis/RabbitMQ containers | pytest + testcontainers/compose | All happy and error paths return correct codes | P1-P3
TS-03 | Contract | OpenAPI schema vs implementation | schemathesis / Dredd | No schema violations | P2
TS-04 | ML evaluation | Held-out test set; per-class metrics; calibration | scikit-learn, MLflow | Meets targets on AI-ML Plan sheet or documented gap analysis | P2-P4
TS-05 | Pipeline correctness | Simulated flood scenario with ground truth | Simulation harness | Dedup + priority + allocation match expected ordering | P3
TS-06 | Idempotency | Replay the same message / report twice | pytest | No duplicate incidents or assignments | P2
TS-07 | End-to-end UI | Citizen report -> authority sees -> assign -> rescue completes | Playwright | Full flow passes in CI | P3-P5
TS-08 | Load | ~1000 virtual users, ~10k reports burst | Locust / k6 | Report-submit P95 latency under 500 ms (ack only, planning target); zero lost messages | P5
TS-09 | Queue stress | Burst > worker capacity; observe backlog drain | Locust + RabbitMQ UI | Backlog drains; queue lag reported; no crashes | P5
TS-10 | Resilience / chaos | Kill worker, DB, broker, Redis mid-load | docker kill / compose stop | Auto-retry/recovery; no data loss; clear errors | P5
TS-11 | Security (OWASP) | Injection, broken access control, auth, file upload, rate-limit bypass | OWASP ZAP, manual checklist, pip-audit / npm audit | No critical or high findings open | P5
TS-12 | Authorization matrix | Every endpoint x every role | Automated matrix test | Matches RBAC matrix exactly | P1-P5
TS-13 | Performance (DB) | Query plans for top queries | EXPLAIN ANALYZE | No sequential scans on hot paths at 100k rows | P5
TS-14 | Usability | Walkthrough with 3-5 classmates/faculty | Task-based observation | Core tasks completed without help | P4-P5
TS-15 | Disaster demo rehearsal | Scripted scenario on seeded data, offline | Manual | Runs end-to-end twice without intervention | P6

## Risks
Risk Register
Score = Likelihood x Impact. Rating: 15+ High, 8-14 Medium, below 8 Low. Edit blue values.
ID | Risk | Likelihood (1-5) | Impact (1-5) | Score | Rating | Mitigation | Trigger / Early Warning
R-01 | Scope too large for timeline | 4 | 5 | 20 | High | Phase gating with demos; MoSCoW; cut Could items first; Version-1 = Phases 0-3. | Phase slips > 1 week
R-02 | Insufficient labeled data for ML | 4 | 4 | 16 | High | Use public crisis datasets + synthetic generator; keep baselines simple; document limits. | F1 far below target after baseline
R-03 | Hardware too weak for local LLM / CV | 3 | 3 | 9 | Medium | Pick smaller model; use CPU-friendly models; Colab free tier for training; LLM features are 'Could'. | Inference latency > 10 s
R-04 | Geocoding rate limits / inaccurate locations | 4 | 3 | 12 | Medium | Cache in Redis, local gazetteer fallback, allow manual pin on map. | Frequent 429 / null coordinates
R-05 | Duplicate threshold merges distinct incidents | 3 | 4 | 12 | Medium | Combine similarity with geo + time; tune on labeled pairs; allow authority to unmerge. | Authority corrections spike
R-06 | Team availability / exams | 4 | 4 | 16 | High | Buffer weeks; role redundancy; weekly sync; avoid single-owner critical tasks. | Missed two consecutive standups
R-07 | Integration complexity (many services) | 3 | 4 | 12 | Medium | Docker Compose from week 2; contract-first APIs; CI integration tests. | Works-on-my-machine reports
R-08 | Security flaws in public reporting endpoint | 3 | 4 | 12 | Medium | Rate limits, validation, upload checks, audit logs, ZAP scan; document remaining abuse risks. | Spam bursts in logs
R-09 | Free-tier hosting changes or unavailable | 3 | 3 | 9 | Medium | Local deployment as primary; recorded demo video; compose-based portability. | Provider quota/availability change
R-10 | LLM hallucination in summaries | 3 | 3 | 9 | Medium | Ground prompts in DB facts; schema validation; label output as AI-generated; human review. | Rubric review finds unsupported claims
R-11 | Dataset licence / terms issues | 2 | 3 | 6 | Low | Check licences up front; cite sources; prefer permissive datasets and synthetic data. | Unclear licence on a dataset
R-12 | Demo failure on evaluation day | 2 | 5 | 10 | Medium | Seeded offline data, scripted flow, backup video, rehearsed twice, spare laptop. | Any failure during rehearsal

## Viva Prep
Viva Preparation: Likely Questions
Draft answer outlines. Rehearse in your own words with real numbers from your tests.
Likely Question | Answer Outline | Tip
Why event-driven / message queue instead of direct processing? | Bursty disaster traffic; decouple fast ingest from slow AI; retries and DLQ; worker scaling; user gets 202 immediately. | Mention at-least-once delivery and idempotency.
Why not microservices for everything? | Modular monolith + workers gives clean boundaries with lower ops cost for a small team; modules can be split later. | Show module boundaries in HLD.
How do you detect duplicate reports? | Multilingual embeddings + cosine similarity + geo-radius + time window; threshold tuned on labeled pairs; authority can unmerge. | Quote precision/recall from tuning report.
How is priority computed? Why trust it? | Transparent weighted score with per-factor breakdown; weights configurable; sensitivity analysis; human approval for dispatch. | Open the Priority Model sheet logic.
How is resource allocation optimal? | Cost matrix (distance) solved with Hungarian algorithm; constraints on type and availability; deterministic and tested. | State limitation: no live traffic.
Where does the LLM fit, and what if it hallucinates? | Only summaries and NL-to-filter; grounded in DB facts; schema-validated; advisory; never auto-dispatches. | Contrast with testable classical models.
What if the AI misclassifies a critical case? | Confidence shown; low-confidence routed for review; CRITICAL recall prioritized; authority override logged and used for retraining. | Cite CRITICAL recall result.
How do you handle security? | JWT with refresh, argon2/bcrypt, deny-by-default RBAC, rate limits, upload validation, audit logs, OWASP/ZAP testing. | Mention remaining abuse risk of public reporting.
How does it scale? | Stateless API replicas, queue buffering, worker scaling, Redis cache, DB indexing; load-test numbers as evidence. | Show Grafana screenshots.
What is the CAP / consistency trade-off? | Eventual consistency for AI-enriched fields; strong consistency for core transactions in PostgreSQL. | Explain 'processing' UI state.
How did you evaluate the ML models? | Held-out test set, macro-F1, per-class recall, confusion matrix, calibration; real vs synthetic data caveat. | Be honest about dataset limits.
How is it different from existing tools? | Combines automated triage, deduplication, explainable prioritization and allocation recommendations in one open-source stack. | Reference literature survey gaps.
What are the limitations and future work? | Public-endpoint abuse controls, road-network routing, SMS/WhatsApp ingest, larger real datasets, multi-city deployment. | Shows maturity.
How did you make this INR 0? | Open-source stack, local LLM/embeddings, OpenStreetMap, free CI, local/free-tier hosting. | Point to Tech Stack sheet.
What did you personally build/own? | Prepare a per-member ownership list tied to Task Plan Assignee column. | Keep consistent with commit history.